## Sheet1
# | Document Name | System Funtion | Progress 1stPhase | Time Needed | Review | Review Time | Time used | Budget | Progress
| CompanyV1 | System company controls | 100% | 2 |  | 2 | 2 | 2 | Reduced from 12
| ePartVesioningOverviewV1 | SVN review relative to ePart | 100% | 2 | 1 | 1 | 3 | 0 | Reduced from 6 hours
| GeneralVx | General purpose support functions | Review if needed | 2 |  | 2 | 0 | 4 | May be removed
| ePartVesioningOverviewVx | Overview of SVN source code repository | 100% | 3 |  | 1 | 4 | 0 | Reduced from 8 hours
| SalesDecisionSupportVx | Catalogue Lookup | 100% | 17 |  | 2 | 19 | 0
| Sales OrderVx | Customer sales | 100% | 11 |  | 1 | 11 | 1
| BuyOutVx | Buy-out non stock items | 100% | 9 |  | 1 | 5 | 5
| SalOrderSplitV1 | Split large S/Orders into picking | 100% | 1 |  | 1 | 1 | 1 | Reduced from 10 hours
| Customer2SalespersonAllocVx | Cust to sales sharing | 100% | 4 |  | 1 | 2 | 3
| CatalogueMaintenanceVx |  | 100% | 17 |  | 3 | 18 | 2 | This document covers a extensive part of ePart & may require additional time to complete
|  | Supplier catalogues |  |  |  |  | 0 | 0
|  | Catalogue register and tracker |  |  |  |  | 0 | 0
|  | Supplier price list import & recalc |  |  |  |  | 0 | 0
|  | Currency conversions |  |  |  |  | 0 | 0
|  | Catalogue assembly – images |  |  |  |  | 0 | 0
|  | Industry parts linking |  |  |  |  | 0 | 0
|  | Supplier barcodes |  |  |  |  | 0 | 0
Wholesale factors
Auto retail factors
Stock journal to adjust AUC pricing
| IndentShippingVx | Tracking import shipments | 100% | 1 |  | 1 | 2 | 0 | Reduced form 6 hours
| NAAMSAVx | Capturing industry stats | 100% | 1 |  | 1 | 2 | 0 | reduced number of hours
| StockWorkbenchV1 | Stock modelling | 100% | 4 |  | 1 | 4 | 1 | Reduced time
| SupplierOrdersVx | Purchasing decison support | 90% | 1 |  | 1 | 1 | 1 | Reduced from 10 hours
| WarehouseVx |  | 100% | 15 |  | 2 | 15 | 2
|  | Stock put-away - binning |  |  |  |  | 0 | 0
|  | Stock movement between bins |  |  |  |  | 0 | 0
|  | Multi-parts per bin |  |  |  |  | 0 | 0
|  | Multiple bins per part |  |  |  |  | 0 | 0
| IntegratedScaleVx | Courier parcel weights | 100% | 3 |  | 1 | 4 | 0 | The appliation has been abandoned and hardware remove
| PosVx | Point of sales | 100% | 6 |  | 2 | 8 | 0
| PosInstallationVx | Installtion how to | 100% | 4 |  | 1 | 4 | 1
| PickingVx | Consolidated picking | 100% | 12 |  | 2 | 14 | 0 | Add ER diagrams, exe and final 1st phase review
Picking controls
Pick checking and verification
Pack and invoicing
| WarehouseReceivingVx | GRV, Supplier ctrl, prod ctrl | 100% | 4 |  | 2 | 4 | 2 | Time adjusted from 16 hrs
| ReceivingJobExceptionsVx | Receiving job exceptions control | 100% | 2 |  | 1 | 2 | 1 | reduced from 10 to 2 hours
| ReturnsToVendorVx | Pre & post putaway | 90% | 3 |  | 1 | 3 | 1 | Reduced form 10 hours
| ReturnsForCreditVx | Debtor returns for credit | 90% | 2 |  | 1 | 2 | 1 | Reduced from 12 hours
| ReceiveLabelJobsVx | Job labellling measurements |  | 1 |  | 1 | 0 | 2
| DespatchingVx | Outbound scheduling & control | 95% | 18 |  | 2 | 18 | 2 | Add ER diagrams, exe and final 1st phase review
| DoorScanningVx | Control freight at courier handover | 95% | 12 |  | 2 | 12 | 2 | Add ER diagrams, exe and final 1st phase review
Local deliveries
| ClaimsVx | Claims on supplier tracking and payment release | 90% | 2 |  | 2 | 2 | 2 | Reduced time from 20 hours - completed basic overview narrative Non trivial solution due to supplier settlement permutations
| PODScanningVx | Scan capture signed POD's | 100% | 2 |  | 1 | 2 | 1 | Time reduced from 14 hours. Limited narative provided
| StockJournalsVx | Stock adjustment journals | 100% | 1 |  | 1 | 1 | 1 | Time reduced from 8 hours
| StockTakeCycleVx | Cycle counts | 100% | 4 |  | 1 | 2 | 3 | Reduced content and hours
| StockTakeW2WVx | Wall to wall | 100% | 4 |  | 1 | 2 | 3 | Reduced content and hours
| CatalogueIntegration | Alert & PI catalogue integration | To Start | 9 |  | 1 | 0 | 10
| ReportingVx | All major reports | To Start | 30 |  | 3 | 0 | 33 | This is a major uncertainty & requires a visit with each user and to ascertain reports used
| SundryVx | Provision for unknown programs & funcitons |  | 30 |  | 5 | 0 | 35 | Due to a period of time where funcitonality was enhanced outside of a controlled senvironment, the extent of funcitonality is not exact and provided for here, A visit with each user is required to determine the full extent
Now forms part of Sage X3 largely
| Debtors maintenance | X3 functionality | To Start | 6 |  | 1 | 0 | 7
| IncidentloggingVx | Track customer arrangements etc | To Start | 6 |  | 1 | 0 | 7
| Creditors maintenance | X3 functionality | To Start | 6 |  | 1 | 0 | 7
| Cashbook | X3 functionality | To Start | 0 |  | 0 | 0 | 0 | Unknown
| General ledger | X3 functionality | To Start | 0 |  | 0 | 0 | 0 | Unknown
[6 empty] | 49 | 160 | 88